## Daily Progress
🚀 6-Week Intern Training Progress Tracker
Python (FastAPI) · React (TanStack) · Docker · GCP ¦ 30 days · 8 hrs/day
Day | Week | Topic / Focus | Daily Task (What to do) | Measurable Target | Status | Date Completed | GitHub Pushed? | Self Evaluation | Concepts Learned
WEEK 1 – Git & Python Fundamentals
1 | Week 1 | Environment Setup | Install Git, Python, VS Code; create & clone GitHub repo | All 3 tools verified; repo cloned locally | Completed | 08.06.2026 | Yes | 5 | • What software development is; the role of an intern; how a dev machine is set up • Installing Git (Windows/macOS/Linux); what version control is and why it matters • Installing Python 3.12+; verifying with python --version • Introduction to the terminal/command line: cd, ls/dir, mkdir • Installing VS Code + Python extension; configuring the integrated terminal
2 | Week 1 | Git Fundamentals & First Python Program | Create hello.py with variables; make 3 separate commits & push | 3+ commits visible on GitHub; hello.py runs | Completed | 08.06.2026 | Yes | 5 | • Git mental model: working directory, staging area, commit history • Core commands: git add, git commit, git status, git log, git push • Connecting a local repo to a GitHub remote; the push/pull cycle • Writing your first Python script: print(), comments, running a .py file • Variables and basic data types: int, float, str, bool
3 | Week 1 | Conditional Statements | Build 4 mini-programs: number classifier, grade calc, login check, largest-of-3 | Grade calc returns correct letters for boundary values | Completed | 09.06.2026 | Yes | 5 | • Boolean logic: True/False and comparison operators (==, !=, <, >, <=, >=) • if, elif, else - the structure of decisions • Logical operators: and, or, not • Nesting conditions; common beginner mistakes (= vs ==, indentation) • Reading input with input() and type conversion
4 | Week 1 | Loops (Repetition) | Build loops.py: multiplication table, sum 1-100, FizzBuzz, guessing game | FizzBuzz correct for all 50 numbers; guessing game loops correctly | To Do |  | No
5 | Week 1 | Data Structures & Functions | Build Contact Book (dict) and To-Do List (list) with functions | All functions work; Week 1 code organized and pushed | To Do |  | No
WEEK 2 – OOP, Tooling & FastAPI REST APIs
6 | Week 2 | OOP Part 1 – Classes & Objects | Write Student class + BankAccount class with deposit/withdraw | BankAccount tracks balance correctly across operations | To Do |  | No
7 | Week 2 | OOP Part 2 – Inheritance & Encapsulation | Build Animal/Dog/Cat hierarchy + Shape/Rectangle/Circle with area() | Polymorphic loop calls speak(); area() returns correct values | To Do |  | No
8 | Week 2 | Modules, Errors & Virtual Environments | Reorganize code into modules; add error handling; create venv with pip & uv | requirements.txt generated; NOTES.md explains pip vs uv | To Do |  | No
9 | Week 2 | Intro to APIs & FastAPI Setup | Build FastAPI app with GET / and GET /hello/{name}; test on /docs | Server runs; /docs accessible; both endpoints return JSON | To Do |  | No
10 | Week 2 | Building REST APIs – CRUD & Pydantic | Full CRUD API for 'tasks': POST/GET/PUT/DELETE with Pydantic models | Create-Read-Update-Delete cycle works through Swagger | To Do |  | No
WEEK 3 – Databases & Real-Time Backend
11 | Week 3 | SQL Fundamentals & PostgreSQL Setup | Create 'users' table; insert 5 rows; write 5 SELECT queries with WHERE/ORDER BY | Database created; queries return filtered/sorted results | To Do |  | No
12 | Week 3 | Advanced SQL – Relationships & Joins | Add 'posts' table (foreign key); write INNER JOIN, LEFT JOIN, GROUP BY | JOINs return correctly related data; counts verified | To Do |  | No
13 | Week 3 | SQLAlchemy ORM | Recreate users/posts as SQLAlchemy models; full CRUD through ORM | Relationship query (user.posts) returns related rows | To Do |  | No
14 | Week 3 | Alembic Migrations & DB-backed API | Add Alembic; autogenerate migration; refactor tasks API to use PostgreSQL | Tasks persist across server restarts; migration files pushed | To Do |  | No
15 | Week 3 | WebSockets & Server-Sent Events (SSE) | Add WebSocket echo/broadcast endpoint + SSE live-counter endpoint | Browser/client receives live messages from both endpoints | To Do |  | No
WEEK 4 – Web Foundations & React
16 | Week 4 | Web Foundations – HTML & CSS | Build responsive personal profile page with semantic HTML + Flexbox CSS | Page renders correctly and adapts to narrow/wide screens | To Do |  | No
17 | Week 4 | JavaScript Fundamentals | Add theme toggle, dynamic list, and fetch() to public API on profile page | Theme toggle, dynamic list, and API fetch all functioning | To Do |  | No
18 | Week 4 | TypeScript & Vite Project Setup | Scaffold Vite + React + TS; rewrite a JS snippet with TypeScript interface | Dev server runs; typed function/interface compiles with no errors | To Do |  | No
19 | Week 4 | React – Components, Props & State | Build Counter (useState), reusable Card (props), and List (.map()) components | Counter updates on click; cards render from props; list maps correctly | To Do |  | No
20 | Week 4 | React Hooks, Tailwind CSS & Forms | Install Tailwind; build controlled form; add useEffect on mount | Styled form adds items to live list; Week 4 pushed | To Do |  | No
WEEK 5 – Fullstack, Docker & Final Assessment
21 | Week 5 | TanStack Query & Router | Connect React to tasks API with useQuery/useMutation; add 2 routes | Tasks load from FastAPI; creating a task updates UI automatically | To Do |  | No
22 | Week 5 | Fullstack Integration – CORS, Real-time & Auth Basics | Enable CORS; wire React to WebSocket/SSE; move URLs to env vars; restructure repo | CORS resolved; live updates appear in React UI without refresh | To Do |  | No
23 | Week 5 | Docker – Containerizing the Application | Write Dockerfiles for backend & frontend; create docker-compose with Postgres | All 3 services start; app works inside containers | To Do |  | No
24 | Week 5 | GitHub Actions (CI/CD) & Assessment Kickoff | Add CI workflow (.github/workflows); write PROJECT_PLAN.md | Actions run green on push; project plan approved by mentor | To Do |  | No
25 | Week 5 | ⭐ FINAL ASSESSMENT – Fullstack Build & Docker Deploy | Build fullstack app meeting full rubric; tag v1.0 release; demo to mentor | App meets all rubric requirements; v1.0 tagged and demoed | To Do |  | No
WEEK 6 – Google Cloud Platform (GCP)
26 | Week 6 | GCP Fundamentals & Account Setup | Create GCP project; run gcloud commands; create service account with IAM role | Project created; gcloud commands run; IAM role assigned | To Do |  | No
27 | Week 6 | Compute & Storage on GCP | Create Cloud Storage bucket; explore Compute Engine / Cloud Run | Bucket holds uploaded object; compute resource created and stopped | To Do |  | No
28 | Week 6 | Deploying to Cloud Run | Push Docker image to Artifact Registry; deploy to Cloud Run | Backend reachable at a public Cloud Run URL | To Do |  | No
29 | Week 6 | GCP Services, Monitoring & Best Practices | View Cloud Logging; set budget alert; tighten IAM roles; write best-practices summary | Logs visible for live service; budget alert configured | To Do |  | No
30 | Week 6 | ☁️ Cloud Capstone, Review & Next Steps | Deploy full stack to GCP (or document steps); write architecture diagram + reflection | Final README + architecture diagram pushed; retrospective submitted | To Do |  | No
Legend: Status → To Do ¦ In Progress ¦ Done ¦ Skipped Self Score: 1=Didn't understand 3=Got it with help 5=Totally confident

## Weekly Summary
📊 Weekly Progress Summary
Update your Daily Progress sheet — this table summarizes completion by week
Week | Focus Area | Days (Total) | Days Done | Completion % | GitHub Push % | Key Milestone
Week 1 | Git & Python Fundamentals | 5 | 0 | 0% | 0% | Working Python programs in GitHub
Week 2 | OOP, Tooling & FastAPI REST APIs | 5 | 0 | 0% | 0% | Full CRUD REST API
Week 3 | Databases & Real-Time Backend | 5 | 0 | 0% | 0% | DB-backed API with real-time endpoints
Week 4 | Web Foundations & React | 5 | 0 | 0% | 0% | Styled interactive React app
Week 5 | Fullstack, Docker & Assessment | 5 | 0 | 0% | 0% | Final fullstack app + Docker deploy ⭐
Week 6 | Google Cloud Platform (GCP) | 5 | 0 | 0% | 0% | App deployed to GCP ☁️
TOTAL / AVERAGE |  | 30 | 0 | 0%
💡 Tip: Update 'Days Done' and 'GitHub Push %' each Friday with your mentor.

## Milestone Checklist
✅ Weekly Milestone Checklist
WEEK 1 – Git & Python Fundamentals
# | Milestone Criterion | Done? | Date | Mentor Comment
1 | Git installed; daily pushes working | ☐ No
2 | Writes conditionals and loops independently | ☐ No
3 | Uses functions, lists, and dictionaries | ☐ No
4 | FizzBuzz and contact book complete | ☐ No
WEEK 2 – OOP, Tooling & FastAPI REST APIs
# | Milestone Criterion | Done? | Date | Mentor Comment
1 | Builds classes with inheritance | ☐ No
2 | Manages a venv (pip and uv) | ☐ No
3 | Runs a FastAPI server with /docs | ☐ No
4 | Full tasks CRUD API working | ☐ No
WEEK 3 – Databases & Real-Time Backend
# | Milestone Criterion | Done? | Date | Mentor Comment
1 | Writes SQL queries and joins | ☐ No
2 | Models data with SQLAlchemy | ☐ No
3 | Runs Alembic migrations; data persists | ☐ No
4 | WebSocket and SSE endpoints working | ☐ No
WEEK 4 – Web Foundations & React
# | Milestone Criterion | Done? | Date | Mentor Comment
1 | Builds a responsive HTML/CSS page | ☐ No
2 | Uses JS DOM, events, and fetch | ☐ No
3 | Scaffolds a typed Vite + React app | ☐ No
4 | Components, hooks, Tailwind, and forms working | ☐ No
WEEK 5 – Fullstack, Docker & Assessment
# | Milestone Criterion | Done? | Date | Mentor Comment
1 | TanStack Query/Router integrated | ☐ No
2 | Fullstack app connected with CORS + live data | ☐ No
3 | docker-compose runs the full stack | ☐ No
4 | CI passes; final app submitted and demoed ⭐ | ☐ No
WEEK 6 – Google Cloud Platform (GCP)
# | Milestone Criterion | Done? | Date | Mentor Comment
1 | GCP project + IAM configured | ☐ No
2 | Provisions compute and storage | ☐ No
3 | Deploys a container to Cloud Run | ☐ No
4 | Reviews logging/monitoring; capstone documented ☁️ | ☐ No

## How To Use
📖 How to Use This Tracker
DAILY PROGRESS (Sheet 1)
──────────────────────────────────────────────────────────────
1. Each row = one day of your training.
2. Update the STATUS column using the dropdown:
• To Do → not started yet
• In Progress → currently working on it
• Done → fully completed ✓
• Skipped → intentionally skipped (discuss with mentor)
3. Fill DATE COMPLETED when you finish a day.
4. Mark GITHUB PUSHED? as Yes/No once you push your daily commit.
5. Rate yourself (SELF SCORE 1–5):
1 = Didn't understand at all
2 = Understood a little
3 = Got it with help
4 = Mostly confident
5 = Totally confident, could explain it to someone else
6. Use NOTES / BLOCKERS to write down anything confusing or interesting.
WEEKLY SUMMARY (Sheet 2)
──────────────────────────────────────────────────────────────
• Update 'Days Done' column each Friday.
• Update 'GitHub Push %' (e.g., 4 out of 5 days = 80%).
• Share this sheet with your mentor every week.
MILESTONE CHECKLIST (Sheet 3)
──────────────────────────────────────────────────────────────
• At the end of each week, go through the checklist with your mentor.
• Change 'Done?' from ☐ No → ☑ Yes when you and your mentor agree it's complete.
• Your mentor can add comments in the last column.
TIPS
──────────────────────────────────────────────────────────────
✦ Fill in this sheet EVERY DAY — even just 2 minutes at end of day.
✦ Be honest about your self-score; it helps your mentor help you.
✦ A score of 3 is perfectly fine — learning takes time!
✦ If you're stuck for more than 30 minutes on something, write it in Notes.
✦ Show this to your mentor at every weekly standup.